## EDP-Estimate-Final
Sr. No. | Screens | Comments | Only UI Design Estimate (man days) | Integration with Datasource (Only Load data from datasource) Estimate (man days) | Total (UI Design + Load data from Datasource) Estimate (man days) | Integration with Datasource (Load+Save from/into datasource) Estimate (man days) | Total (UI Design + Load/Save from Datasource) Estimate (man days) | Data fields
Insights Demand Creation App |  | Tablet/Desktop Device
1 | Splash Screen (EDP-01) | 1. continue - Navigate 2. exit - Navigate | 1 | 0 | 1 | 0 | 1
2 | Demand Dashboard (List/Search of Demands) (EDP-02) | 1. Search - show only message "feature is not yet available ….." 2. List 3. Create new demand - Navigate 4. Exit - Navigate | 4 | 1 | 5 | 2 | 6
3 | Demand Create - Details (EDP-03) | 1. 12 fields - only few fields are simple and rest are medium 2. Cancel button - Navigate 3. Save button - check for mandatory fields, save and navigate to dashboard screen 4. Different field level buttons e.g. active days, person, activities, and so on.. 5. Rendering values selected from other screens e.g. active days and times. | 8 | 2 | 10 | 6 | 14 | Fields - Reference (NULL, Non Editable) - Title (Mandatory) - Description (Mandatory) - The Creating User (Non-editable, defaulted to the Current User) - Type (Mandatory) - Ownership Type (Staff Member or Team, Mandatory) - Enabled - (Mandatory, defaulted to Enabled) - Select Active Days and Times (defaulted to all day on every day of the week, Mandatory) - Select Person Selection (Option) - Location Type (Fixed Location / Geographical Area, Mandatory) - Required Activities (At least one entry is mandatory, Required Activity Text and Possible Results for each) - Repeat Intervals (Mandatory)
4 | Demand Create - Select Person (RMS/Manual) | 1. Manual - show only message "feature is not yet available ….." 2. From RMS - Navigate 3. Cancel button - Navigate | 1 | 0 | 1 | 0 | 1
5 | Demand Create - Select Person from RMS (EDP-06) | 1. Person List 2. Search - based on surname, forename, DOB or RMS ID. Add validations. 3. Exit button - Navigate 4. Select button against each record on the list - Navigate | 2 | 1 | 3 | 3 | 5 | Person fields: surname, forename, DOB. RMS ID
6 | Demand Create - Select Staff (EDP-04) | 1. Staff List 2. Search - based on Rank, Collar Number and Surname fields. Add validations. 3. Cancel button - Navigate 4. Select button against each record on the list - Navigate | 3 | 0 | 3 | 3 | 6 | Staff fields: Collar number, surname
7 | Demand Create - Select Location | 1. Fixed - Navigate 2. Area - Navigate 3. Cancel button - Navigate | 1 | 0 | 1 | 0 | 1
8 | Demand Create - Select Location - Fixed Location (EDP-07) | 1. Fields: i. Search Textfield - show lookup for the matched locations and set pin on the maps ii. Maps - allow user to set pin iii. Radius Textfield 2. Save - save/navigate 3. Cancel button - Navigate | 5 | 0 | 5 | 3 | 8 | Fixed Location - LocationText, Radius
9 | Demand Create - Select Location - Area Location (EDP-08) | 1. Maps - Actions: i. show already selected ii. option to select area - draw polygon iii. Exit - navigate iv. clear v. save - validations/save/navigate 2. Cancel button - Navigate | 10 | 0 | 10 | 6 | 16
10 | Demand Create - Select Activities (with save) | 1. Static Activity List 2. Allow user to choose applicable activities for this demand (multi-select) 3. Save - Save/Navigate 4. Cancel button - Navigate | 2 | 1 | 3 | 3 | 5
11 | Demand Create - Select Activities - Select Actions (with save actions) | 1. Static Response List to be shown for each activity 2. Allow user to choose applicable activities for this demand (multi-select) 3. Save - Save/Navigate 4. Cancel button - Navigate | 2 | 1 | 3 | 2 | 4
12 | Demand Create - Active Days & Times (EDP-05) | 1. Days of the week 2. Each day will be presented with five options with single select 3. Save button - mandatory validation check, save multiple records and navigate 4. Cancel button | 4 | 0 | 4 | 5 | 9
13 | Demand View (EDP-09) (incl any responses) | 1. Show summary of the demand (fields for each item is mentioned on pg. 29) 2. View more details - show more fields with the respond button 3. Respond button against each activity - Navigate | 6 | 1 | 7 | 5 | 11
14 | Demand View - Show Response Details (EDP-14) | 1. Show list of responses associated to selected activity 2. Close - Navigate | 3 | 1 | 4 | 1 | 4
Community Insights App |  | Mobile/Tablet Device |  |  |  |  | 0
15 | Splash Screen (EDP-10) | 1. continue - Navigate 2. exit - Navigate | 1 | 0 | 1 | 0 | 1 | copy of insight creation app
16 | Map View (EDP-11) | 1. Maps - following need to be plotted on the map i. Current location of the device* ii. Any fixed location demands iii. Any geographical area iv. Any tasks - Navigate v. Any investigations - Navigate vi. Any intelligence reports - Navigate vii. Any CAD incidents - Navigate 2. List view - Navigate 3. Exit button - close the app 4. Select Demand for fixed location demand or geographical area demand - Navigate to Record View | 13 | 4 | 17 | 10 | 23 | 1. Assumption is to show pins of the nearest fixed location demands? 2. how the locations for tasks, investigations, intelligence and CAD incidents are created and to be shown? Similar to the demand pins?
17 | Map View - Show summary record | 1. Show demand summary (for demand, task, and 3 others) 2. More Detail button - Navigate to Record View 2. Close button - Navigate | 6 | 1 | 7 | 3 | 9
18 | List View (EDP-12) | 1. Gallery view for the following items (fields for each item is mentioned on pg. 28): - Any fixed location demands - Any geographical area demands that are enabled - Any Tasks - Any Investigations - Any Intelligence reports - Any CAD Incidents 2. Map View - Navigate 3. Exit button - close the app 4. More Detail button against each item - Navigate to Record View 5. all items should also have the distance from current location listed in metres (except Geo Location Demands) | 10 | NA | 10 | 5 | 15
19 | Record View (EDP-13) (Demand Details incl any responses) | 1. Show summary of the demand (fields for each item is mentioned on pg. 29) 2. View more details - show more fields with the respond button 3. Respond button - Navigate | 4 | 0 | 4 | 3 | 7 | similar to Demand View screen of Inisghts Demand Creation app
20 | Demand Response (EDP-14) | 1. 6 fields to be shown (refer pg. 30) 2. Save Response - mandatory validation check/save/navigate - Integration with datasource 3. Exit - Navigate | 4 | 0 | 4 | 2 | 6
Common | [6 empty] | 0
1 | Choose datasource and design data structure for EDP (Sharepoint or Spreadsheet) |  | 0 | 0 | 0 | 3 | 3
2 | Styling/Responsive/Env Setup |  | 0 | 0 | 0 | 0 | 0
3 | Unit Testing (integration testing, responsive, flow check, etc) |  | 0 | 2 | 0 | 5 | 5
4 | App icon on mobile | Need to check
Total Dev Efforts |  |  | 90 | 15 | 105 | 70 | 160
Manual Testing Efforts (25% of Dev efforts) |  |  | 23 |  | 26 |  | 40
|  | Dev | Weeks Required (with 2 powerapp dev) |  |  |  | Weeks Required (with 2 powerapp dev)
|  |  | 9 |  |  |  | 16

## Loading
Only UI Design
| 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks |  | Efforts in person days
| Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5
Development | 20 | 20 | 20 | 20 | 20 | Dev | 100 | 12000
Testing | [5 empty] | Test | 0
| 1 week | 2 weeks | 2 weeks | 2 weeks | 1 week | 2 weeks | 2 weeks | 1 week | 1 week
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Stabilization Sprint | Sprint 4 | Sprint 5 | UAT Support | GO LIVE Support
Devs | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1
Tester |  |  | 1 | 1 | 1 | 1 | 1 | 1
Effort Person days
| Sprint 0 | 10 |  |  |  | 24000
| Development Sprints (5) | 140 |  |  |  | 18000
150
UI Design +Load/ Save
Stabilization Sprint
| 1 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 4 weeks | 2 weeks |  | Efforts in person days | UAT Support
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | UAT Support | GO LIVE Support |  |  | 5
Development | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | Dev | 170 | 5
Testing |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 20 |  | Test | 90
| 1 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks | 4 weeks | 2 weeks |  |  | UAT Support
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | UAT Support | GO LIVE Support |  |  | 5
dev | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 1 | 1
Test | [10 empty] | 1 | bar: Sprint 1 to Sprint 9
Effort Person days
| Development Sprints (5) | 240
| Stabilization Sprint | 30
| UAT | 40
| Go LIVE Support | 10 |  |  | 38400
320
| 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks |  | Efforts in person days
| Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5
Development | 30 | 30 | 30 | 30 | 30 | Dev | 150
Testing | 10 | 10 | 10 | 10 | 10 | Test | 50
| 2 weeks | 2 weeks | 2 weeks | 2 weeks | 2 weeks
| Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5
Devs | Sprint 0: 3; Sprint 1: 3; Sprint 2: 3; Sprint 3: 3; Sprint 4: 3
Tester | bar: Sprint 0 to Sprint 4
Effort Person days
| Development Sprints (5) | 140
140

## EDP-Estimate-Old (hidden)
Sr. No. | Screens | Comments | Development Size | Only UI Design Estimate (man days) | Integration with Datasource Estimate (man days) | Total (UI Design + Datasource Integration Load/Save) Estimate (man days) | Data fields
Insights Demand Creation App |  | Tablet/Desktop Device
1 | Splash Screen | 1. continue - Navigate 2. exit - Navigate | Small | 1 | NA | 1
2 | Demand Dashboard (List/Search of Demands) | 1. Search - show only message "feature is not yet available ….." 2. List 3. Create new demand - Navigate 4. Exit - Navigate | Medium | 4 | 2 | 6
3 | Demand Create - Details (with save demand) | 1. 12 fields - only few fields are simple and rest are medium 2. Cancel button - Navigate 3. Save button - check for mandatory fields, save and navigate to dashboard screen 4. Rendering values selected from other screens e.g. active days and times. | X-Large | 8 | 6 | 14 | Fields - Reference (NULL, Non Editable) - Title (Mandatory) - Description (Mandatory) - The Creating User (Non-editable, defaulted to the Current User) - Type (Mandatory) - Ownership Type (Staff Member or Team, Mandatory) - Enabled - (Mandatory, defaulted to Enabled) - Select Active Days and Times (defaulted to all day on every day of the week, Mandatory) - Select Person Selection (Option) - Location Type (Fixed Location / Geographical Area, Mandatory) - Required Activities (At least one entry is mandatory, Required Activity Text and Possible Results for each) - Repeat Intervals (Mandatory)
4 | Demand Create - Select Person (RMS/Manual) | 1. Manual - show only message "feature is not yet available ….." 2. From RMS - Navigate 3. Cancel button - Navigate | Small | 1 | NA | 1
5 | Demand Create - Select Person - Search RMS | 1. Person List (hardcoded) 2. Search - based on surname, forename, DOB or RMS ID. Add validations. 3. Exit button - Navigate 4. Select button against each record on the list - Navigate | Medium | 2 | 3 | 5 | Person fields: surname, forename, DOB. RMS ID
6 | Demand Create - Select Staff (assumption - lookup) | 1. Staff List (hardcoded) 2. Search - based on Rank, Collar Number and Surname fields. Add validations. 3. Cancel button - Navigate 4. Select button against each record on the list - Navigate | Medium | 3 | 3 | 6 | Staff fields: Collar number, surname
7 | Demand Create - Select Location | 1. Fixed - Navigate 2. Area - Navigate 3. Cancel button - Navigate | Small | 1 | NA | 1
8 | Demand Create - Select Location - Fixed Location | 1. Fields: i. Search Textfield - show lookup for the matched locations and set pin on the maps ii. Maps - allow user to set pin iii. Radius Textfield 2. Save - save/navigate 3. Cancel button - Navigate | Medium | 5 | 3 | 8 | Fixed Location - LocationText, Radius
9 | Demand Create - Select Location - Area Location | 1. Maps - Actions: i. show already selected ii. option to select area - draw polygon iii. Exit - navigate iv. clear v. save - validations/save/navigate 2. Cancel button - Navigate | X-Large | 10 | 6 | 16
10 | Demand Create - Select Activities (with save) | 1. Static Activity List 2. Allow user to choose applicable activities for this demand (multi-select) 3. Save - Save/Navigate 4. Cancel button - Navigate | Medium | 2 | 3 | 5
11 | Demand Create - Select Activities - Select Actions (with save actions) | 1. Static Response List to be shown for each activity 2. Allow user to choose applicable activities for this demand (multi-select) 3. Save - Save/Navigate 4. Cancel button - Navigate | Medium | 2 | 2 | 4
12 | Demand Create - Active Days & Times (with save) | 1. Days of the week 2. Each day will be presented with five options with single select 3. Save button - mandatory validation check, save multiple records and navigate 4. Cancel button | Large | 4 | 5 | 9
13 | Demand View - Details (incl any responses). This should be mirror to that of Record View screen of Community Insights | 1. Show summary of the demand (fields for each item is mentioned on pg. 29) 2. View more details - show more fields with the respond button 3. Respond button against each activity - Navigate | Large | 6 | 5 | 11
14 | Demand View - Show Response Details | 1. Show list of responses associated to selected activity 2. Close - Navigate | Medium | 3 | 1 | 4
Community Insights App |  | Mobile/Tablet Device
15 | Splash Screen | 1. continue - Navigate 2. exit - Navigate | Small | 1 | NA | 1 | copy of insight creation app
16 | Map View | 1. Maps - following need to be plotted on the map i. Current location of the device* ii. Any fixed location demands iii. Any geographical area iv. Any tasks - Navigate v. Any investigations - Navigate vi. Any intelligence reports - Navigate vii. Any CAD incidents - Navigate 2. List view - Navigate 3. Exit button - close the app 4. Select Demand for fixed location demand or geographical area demand - Navigate to Record View | X-Large | 13 | 10 | 23 | 1. Assumption is to show pins of the nearest fixed location demands? 2. how the locations for tasks, investigations, intelligence and CAD incidents are created and to be shown? Similar to the demand pins?
17 | Map View - Show summary record | 1. Show demand summary (for demand, task, and 3 others) 2. More Detail button - Navigate to Record View 2. Close button - Navigate | Small | 6 | 3 | 9
18 | List View | 1. Gallery view for the following items (fields for each item is mentioned on pg. 28): - Any fixed location demands - Any geographical area demands that are enabled - Any Tasks - Any Investigations - Any Intelligence reports - Any CAD Incidents 2. Map View - Navigate 3. Exit button - close the app 4. More Detail button against each item - Navigate to Record View 5. all items should also have the distance from current location listed in metres (except Geo Location Demands) | X-Large | 10 | 5 | 15
19 | Record View (Demand Details incl any responses) | 1. Show summary of the demand (fields for each item is mentioned on pg. 29) 2. View more details - show more fields with the respond button 3. Respond button - Navigate | Medium | 4 | 3 | 7 | similar to Demand View screen of Inisghts Demand Creation app
20 | Demand Response (with save response) | 1. 6 fields to be shown (refer pg. 30) 2. Save Response - mandatory validation check/save/navigate - Integration with datasource 3. Exit - Navigate | Medium | 4 | 2 | 6
Common
1 | Choose datasource and design data structure for EDP (Sharepoint or Spreadsheet) |  | Medium | NA | 3 | 3
2 | Styling/Responsive/Env Setup |  | Medium | 5 | NA | 5
3 | Unit Testing (integration testing, responsive, flow check, etc) |  | Large | 5 | 5 | 10
4 | App icon on mobile | Need to check
Total Dev Efforts |  |  |  | 100 | 70 | 170
Manual Testing Efforts (25% of Dev efforts) |  |  |  | 25 | NA | 43
|  | Dev |  | Weeks Required (with 2 powerapp dev) |  | Weeks Required (with 2 powerapp dev)
|  |  |  | 10 |  | 17

## Assumptions
Scope | UI + Load data from Sharepoint
Sr. No | Details | 20 screens - with scope
1 | The data shared by Adam (e.g. staff and person) will be used in the prototypes. | ui - 80 days - 8 weeks
2 | The community insights user can view the saved demands in map view and list view | ui+datasource(load+save) - 16 days
3 | The user can simply view the summary/details for below entities from datasource and cannot record/update any response back to datasource. Tasks Investigations Intelligence CAD Incidents
4 | Both the powerapp apps will have responsive design i.e. Insights Demand Creation App will be accessible from mobile and tablet, while Community Insights App will be accessible from tablet and desktop
5 | The demand created/updated from the prototype won't be saved in datasource (e.g. sharepoint or spreadsheet)
6 | The demands are prefilled in the datasource and the same will be loaded on UI (edit and view screens)

## EDP-Estimate-Initial (hidden)
Sr. No. | Screens | Comments | Development Size | Only UI Design Estimate (man days) | Integration with Datasource Estimate (man days) | Total Estimate (man days) | Data fields
Insights Demand Creation App |  | Tablet/Desktop Device
1 | Splash Screen | 1. continue - Navigate 2. exit - Navigate | Small | 2 | NA | 2 |  | 1
2 | Demand Dashboard (List/Search of Demands) | 1. Search - show only message "feature is not yet available ….." 2. List 3. Create new demand - Navigate 4. Exit - Navigate | Medium | 3 | 2 | 5
3 | Demand Create - Details (with save demand) | 1. 12 fields - only few fields are simple and rest are medium 2. Cancel button - Navigate 3. Save button - check for mandatory fields, save and navigate to dashboard screen 4. Rendering values selected from other screens e.g. active days and times. | X-Large | 10 | 6 | 16 | Fields - Reference (NULL, Non Editable) - Title (Mandatory) - Description (Mandatory) - The Creating User (Non-editable, defaulted to the Current User) - Type (Mandatory) - Ownership Type (Staff Member or Team, Mandatory) - Enabled - (Mandatory, defaulted to Enabled) - Select Active Days and Times (defaulted to all day on every day of the week, Mandatory) - Select Person Selection (Option) - Location Type (Fixed Location / Geographical Area, Mandatory) - Required Activities (At least one entry is mandatory, Required Activity Text and Possible Results for each) - Repeat Intervals (Mandatory)
4 | Demand Create - Select Person (RMS/Manual) | 1. Manual - show only message "feature is not yet available ….." 2. From RMS - Navigate 3. Cancel button - Navigate | Small | 1 | NA | 1
5 | Demand Create - Select Person - Search RMS | 1. Person List (hardcoded) 2. Search - based on surname, forename, DOB or RMS ID. Add validations. 3. Exit button - Navigate 4. Select button against each record on the list - Navigate | Medium | 2 | 3 | 5 | Person fields: surname, forename, DOB. RMS ID
6 | Demand Create - Select Staff (assumption - lookup) | 1. Staff List (hardcoded) 2. Search - based on Rank, Collar Number and Surname fields. Add validations. 3. Cancel button - Navigate 4. Select button against each record on the list - Navigate | Medium | 3 | 3 | 6 | Staff fields: Collar number, surname
7 | Demand Create - Select Location | 1. Fixed - Navigate 2. Area - Navigate 3. Cancel button - Navigate | Small | 1 | NA | 1
8 | Demand Create - Select Location - Fixed Location | 1. Fields: i. Search Textfield - show lookup for the matched locations and set pin on the maps ii. Maps - allow user to set pin iii. Radius Textfield 2. Save - save/navigate 3. Cancel button - Navigate | Medium | 4 | 3 | 7 | Fixed Location - LocationText, Radius
9 | Demand Create - Select Location - Area Location | 1. Maps - Actions: i. show already selected ii. option to select area - draw polygon iii. Exit - navigate iv. clear v. save - validations/save/navigate 2. Cancel button - Navigate | X-Large | 8 | 6 | 14
10 | Demand Create - Select Activities (with save) | 1. Static Activity List 2. Allow user to choose applicable activities for this demand (multi-select) 3. Save - Save/Navigate 4. Cancel button - Navigate | Medium | 3 | 3 | 6
11 | Demand Create - Select Activities - Select Actions (with save actions) | 1. Static Response List to be shown for each activity 2. Allow user to choose applicable activities for this demand (multi-select) 3. Save - Save/Navigate 4. Cancel button - Navigate | Medium | 2 | 2 | 4
12 | Demand Create - Active Days & Times (with save) | 1. Days of the week 2. Each day will be presented with five options with single select 3. Save button - mandatory validation check, save multiple records and navigate 4. Cancel button | Large | 5 | 5 | 10
13 | Demand View - Details (incl any responses). This should be mirror to that of Record View screen of Community Insights | 1. Show summary of the demand (fields for each item is mentioned on pg. 29) 2. View more details - show more fields with the respond button 3. Respond button against each activity - Navigate | Large | 7 | 5 | 12
14 | Demand View - Show Response Details | 1. Show list of responses associated to selected activity 2. Close - Navigate | Medium | 2 | 1 | 3
Community Insights App |  | Mobile/Tablet Device
15 | Splash Screen | 1. continue - Navigate 2. exit - Navigate | Small | 1 | NA | 1 | copy of insight creation app
16 | Map View | 1. Maps - following need to be plotted on the map i. Current location of the device* ii. Any fixed location demands iii. Any geographical area iv. Any tasks - Navigate v. Any investigations - Navigate vi. Any intelligence reports - Navigate vii. Any CAD incidents - Navigate 2. List view - Navigate 3. Exit button - close the app 4. Select Demand for fixed location demand or geographical area demand - Navigate to Record View | X-Large | 15 | 10 | 25 | 1. Assumption is to show pins of the nearest fixed location demands? 2. how the locations for tasks, investigations, intelligence and CAD incidents are created and to be shown? Similar to the demand pins?
17 | Map View - Show summary record | 1. Show demand summary (for demand, task, and 3 others) 2. More Detail button - Navigate to Record View 2. Close button - Navigate | Small | 5 | 3 | 8
18 | List View | 1. Gallery view for the following items (fields for each item is mentioned on pg. 28): - Any fixed location demands - Any geographical area demands that are enabled - Any Tasks - Any Investigations - Any Intelligence reports - Any CAD Incidents 2. Map View - Navigate 3. Exit button - close the app 4. More Detail button against each item - Navigate to Record View 5. all items should also have the distance from current location listed in metres (except Geo Location Demands) | X-Large | 12 | 5 | 17
19 | Record View (Demand Details incl any responses) | 1. Show summary of the demand (fields for each item is mentioned on pg. 29) 2. View more details - show more fields with the respond button 3. Respond button - Navigate | Medium | 3 | 3 | 6 | similar to Demand View screen of Inisghts Demand Creation app
20 | Demand Response (with save response) | 1. 6 fields to be shown (refer pg. 30) 2. Save Response - mandatory validation check/save/navigate - Integration with datasource 3. Exit - Navigate | Medium | 3 | 3 | 6
Common
1 | Choose datasource and design data structure for EDP (Sharepoint or Spreadsheet) |  | Medium | NA | 3 | 3
2 | Styling/Responsive |  | Medium | 5 | NA | 5
3 | Unit Testing (integration testing, responsive, flow check, etc) |  | Large | 5 | 5 | 10
4 | App icon on mobile | Need to check
Total Dev Efforts |  |  |  | 102 | 71 | 173
Manual Testing Efforts (25% of Dev efforts) |  |  |  | 26 | NA | 43
|  | Average |  | 90 |  | 145
|  | Dev |  | Weeks Required (with 2 powerapp dev) |  | Weeks Required (with 2 powerapp dev)
|  |  |  | 10 |  | 17