## Sheet1
Task | Sub-Task | Comments | Estimate (man days)
Admin Console - Screens | Manage Demand Configuration | 13 parameters - 7 medium and rest are simple | 30
| Manage Insights Configuration | 6 parameters - all simple | 5
| Manage Shared / Solution Config | 3 parameters - all medium | 2
| Portal Configuration | 1 parameter - simple | 1
| Broker Configuration | 5/6 parameters - simple Can't test as connector integration is not part of phase 1 | 4
| Splash Screen Configurations for 2 apps | superuser and user | 14
| Log actions/errors/warning | for all the above screens | 30
APIs for SQL (Will finalise in sprint 0) | APIs | 60 | 80
|  | SQL Scripts | 0
Common | Audit/Logging & View | Need to go through existing code and may need to rewrite similar for this project. Audit/Logging will be common for Admin Console & 2 PowerApps | 60
| Dataverse (or SQL) DB Design | Entities Creation | 15
| Software Documentation |  | 0
PowerApps - Common | Env Setup |  | 5
| Custom Connectors | For License Manager, Audit/Logging & for APIs (if developed with SQL) | 30
| Loading configurations | Checking PowerApp Configurations before loading screens | 10
PowerApps - Demand Insignts (Super User) | Login/Licence Manager Check |  | 10
| Splash Screen |  | 10
| Demand - List/Filtering/Sorting |  | 15
| Demand - List Maps |  | 30
| Demand - Create/Edit |  | 25
| Log actions/errors/warning |  | 15
PowerApps - Community Insights (User) | Login/Licence Manager Check | assuming most of the things will be reused from super-user screens | 5
| Splash Screen | assuming most of the things will be reused from super-user screens | 5
| Demand - List/Filtering/Sorting | assuming most of the things will be reused from super-user screens | 10
| Demand - List Maps | assuming most of the things will be reused from super-user screens | 25
| Demand - Edit | assuming most of the things will be reused from super-user screens | 15
| Log actions/errors/warning | assuming most of the things will be reused from super-user screens | 15
Dev Efforts |  |  | 466
Unit Testing & Integration Testing (10% of total dev efforts) | 60 |  | 46.6
Manual Testing (30% of Dev + Unit testing) |  |  | 153.78
DevOps (fixed) |  |  | 100
Total Estimate |  |  | 766.38

## Sheet3
Stabilization Sprint
|  |  | Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14 | Sprint 15 | Sprint 16 | Sprint 17 | Sprint 18
PowerApps - Common | Env Setup, Custom Connectors, Loading configurations | 5
Admin Console - Screens | Manage Demand Configuration | 30
| Manage Insights Configuration | 5
| Manage Shared / Solution Config | 2
| Portal Configuration | 1
| Broker Configuration | 4
| Splash Screen Configurations for 2 apps | 14
| Log actions/errors/warning | 30
0
Common | Audit/Logging & View | 60
| Dataverse (or SQL) DB Design | 15
| Software Documentation | 0
PowerApps - Demand Insignts (Super User) | Login/Licence Manager Check | 10
| Splash Screen | 10
| Demand - List/Filtering/Sorting | 15
| Demand - List Maps | 30
| Demand - Create/Edit | 25
| Log actions/errors/warning | 15
PowerApps - Community Insights (User) | Login/Licence Manager Check | 5
| Splash Screen | 5
| Demand - List/Filtering/Sorting | 10
| Demand - List Maps | 25
| Demand - Edit | 15
| Log actions/errors/warning | 15
Dev Efforts |  | 341
|  |  | Sprint 3: Stabilization Sprint | UAT Support | GO LIVE Support
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14
.Net Dev | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
.Net Dev |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Power App Dev 1 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Power App Dev 2 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
DevOps | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Tester 1 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Tester 2 | Stabilization Sprint Sprint 6: 10; Stabilization Sprint Sprint 7: 10; Stabilization Sprint Sprint 8: 10; Stabilization Sprint Sprint 9: 10 | 10 | 10

## Delivery Plan
Stabilization Sprint
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11
PowerApps - Common (Env Setup, Custom Connectors, Loading Configurations, etc) | bar: Sprint 0 to Sprint 1
Dataverse (or SQL) DB Design | bar: Sprint 0 to Sprint 2
Admin Console - Screens
Manage Demand Configuration | bar: Sprint 3 to Sprint 4
Manage Insights Configuration | bar: Stabilization Sprint Sprint 6 to Stabilization Sprint Sprint 7
Manage Shared / Solution Config | bar: Stabilization Sprint Sprint 6 to Stabilization Sprint Sprint 7
Portal Configuration | bar: Stabilization Sprint Sprint 6 to Stabilization Sprint Sprint 7
Broker Configuration | bar: Stabilization Sprint Sprint 7 to Stabilization Sprint Sprint 8
Splash Screen Configurations for 2 apps | bar: Stabilization Sprint Sprint 5 to Stabilization Sprint Sprint 9
Log actions/errors/warning | bar: Sprint 3 to Stabilization Sprint Sprint 9
Audit Logging and Viewing
PowerApps - Demand Insignts (Super User)
Login/Licence Manager Check | bar: Sprint 2
Splash Screen | bar: Sprint 3
Demand - List/Filtering/Sorting | bar: Sprint 3 to Sprint 4
Demand - List Maps | bar: Sprint 4 to Stabilization Sprint Sprint 6
Demand - Create/Edit | bar: Stabilization Sprint Sprint 7 to Stabilization Sprint Sprint 8
Log actions/errors/warning | bar: Stabilization Sprint Sprint 6 to Stabilization Sprint Sprint 8
PowerApps - Community Insights (User)
Login/Licence Manager Check | bar: Stabilization Sprint Sprint 9
Splash Screen | bar: Stabilization Sprint Sprint 9
Demand - List/Filtering/Sorting | bar: Stabilization Sprint Sprint 9
Demand - List Maps
Demand - Edit
Log actions/errors/warning
| Stabilization Sprint Sprint 5: Stabilization Sprint | Stabilization Sprint
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 |  | Expected Delivery to UAT
PowerApps - Common (Env Setup, Custom Connectors, Loading Configurations, etc) | [13 empty] | PowerApps - Common (Env Setup, Custom Connectors, Loading Configurations, etc) | bar: Sprint 0 to Sprint 1
Dataverse (or SQL) DB Design | [13 empty] | Dataverse (or SQL) DB Design | bar: Sprint 0 to Sprint 2
Admin Console - Screens | [13 empty] | Admin Console - Screens
Manage Demand Configuration | [13 empty] | Manage Demand Configuration | bar: Sprint 3 to Sprint 4
Manage Insights Configuration | [13 empty] | Manage Insights Configuration | bar: Stabilization Sprint Sprint 6 to Stabilization Sprint Sprint 8
Manage Shared / Solution Config | [13 empty] | Manage Shared / Solution Config | bar: Stabilization Sprint Sprint 6 to Stabilization Sprint Sprint 8
Portal Configuration | [13 empty] | Portal Configuration | bar: Stabilization Sprint Sprint 6 to Stabilization Sprint Sprint 8
Broker Configuration | [13 empty] | Broker Configuration | bar: Stabilization Sprint Sprint 7 to Stabilization Sprint Sprint 8
Splash Screen Configurations for 2 apps | [13 empty] | Splash Screen Configurations for 2 apps | bar: Stabilization Sprint Sprint 5 to Stabilization Sprint Sprint 9
Log actions/errors/warning | [13 empty] | Log actions/errors/warning | bar: Sprint 3 to Stabilization Sprint Sprint 9
Audit Logging and Viewing | [13 empty] | Audit Logging and Viewing
PowerApps - Demand Insignts (Super User) | [13 empty] | PowerApps - Demand Insignts (Super User)
Login/Licence Manager Check | [13 empty] | Login/Licence Manager Check | bar: Sprint 2 to Sprint 3
Splash Screen | [13 empty] | Splash Screen | bar: Sprint 3 to Sprint 4
Demand - List/Filtering/Sorting | [13 empty] | Demand - List/Filtering/Sorting | bar: Sprint 3 to Sprint 4
Demand - List Maps | [13 empty] | Demand - List Maps | bar: Sprint 4 to Stabilization Sprint Sprint 6
Demand - Create/Edit | [13 empty] | Demand - Create/Edit | bar: Stabilization Sprint Sprint 7 to Stabilization Sprint Sprint 8
Log actions/errors/warning | [13 empty] | Log actions/errors/warning | bar: Stabilization Sprint Sprint 6 to Stabilization Sprint Sprint 8
PowerApps - Community Insights (User) | [13 empty] | PowerApps - Community Insights (User)
Login/Licence Manager Check | [13 empty] | Login/Licence Manager Check | bar: Stabilization Sprint Sprint 9
Splash Screen | [13 empty] | Splash Screen | bar: Stabilization Sprint Sprint 9
Demand - List/Filtering/Sorting | [13 empty] | Demand - List/Filtering/Sorting | bar: Stabilization Sprint Sprint 9
Demand - List Maps | [13 empty] | Demand - List Maps
Demand - Edit | [13 empty] | Demand - Edit
Log actions/errors/warning | [13 empty] | Log actions/errors/warning

## Loading with Dataverse (hidden)
Actual
| .NEt Developers |  | 160 |  | 240
| Unit Testing |  | 46
| Power App |  | 210 |  | 240
| DevOps |  | 100
Testers
[6 empty] | Stabilization Sprint | [6 empty] | UAT Support | GO LIVE Support |  |  | Effort
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Phase | Duration | person days
.Net Dev | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | Sprint 0 | 2 weeks | 45
.Net Dev |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  | Development efforts | 22 weeks | 655
Power App Dev 1 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | UAT Support | 2 weeks | 35
Power App Dev 2 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  | GO LIVE Support | 2 weeks | 35
DevOps | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | Total | 28 weeks | 760
Tester 1 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Tester 2 | Stabilization Sprint Sprint 6: 10; Stabilization Sprint Sprint 7: 10; Stabilization Sprint Sprint 8: 10; Stabilization Sprint Sprint 9: 10 | 10 | 10
| Stabilization Sprint Sprint 5: Stabilization Sprint |  |  | UAT Support | GO LIVE Support |  |  | Effort
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Phase | Duration | person days
.Net Dev | [10 empty] | 1 | 1 | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
.Net Dev | [10 empty] | 1 | 1 | bar: Sprint 2 to Stabilization Sprint Sprint 9
Power App Dev 1 | [10 empty] | 1 | 1 | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
Power App Dev 2 | [10 empty] | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
DevOps | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Tester 1 | [10 empty] | 1 | 1 | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
Tester 2 | [10 empty] | 1 | 1 | bar: Stabilization Sprint Sprint 6 to Stabilization Sprint Sprint 9
Total Resources | 4.5 | 4.5 | 5.5 | 5.5 | 5.5 | 5.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 3.5 | 3.5

## loading with SQL+Dataverse
Actual
| .NEt Developers |  | 160 |  | 240
| Unit Testing |  | 46
| Power App |  | 210 |  | 240
| DevOps |  | 100
Testers
[5 empty] | Stabilization Sprint |  |  |  |  | Stabilization Sprint |  |  | UAT Support | GO LIVE Support |  |  |  | Effort
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 |  | Phase | Duration | person days
.Net Dev | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  | Sprint 0 | 2 weeks | 45
.Net Dev |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  |  | Development efforts | 22 weeks | 670
Power App Dev 1 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  | UAT Support | 2 weeks | 35
Power App Dev 2 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  |  | GO LIVE Support | 2 weeks | 30
DevOps | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  |  | Total | 28 weeks | 780
Tester 1 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Tester 2 | Stabilization Sprint Sprint 5: 10; Stabilization Sprint Sprint 6: 10; Stabilization Sprint Sprint 7: 10; Stabilization Sprint Sprint 8: 10; Stabilization Sprint Sprint 9: 10 | 10 | 10
100200
[16 empty] | 91200 |  | 670
| Stabilization Sprint Sprint 5: Stabilization Sprint | Stabilization Sprint |  |  | UAT Support | GO LIVE Support |  |  |  | Effort
| Ssprint 0 | Ssprint 1 | Ssprint 2 | Ssprint 3 | Ssprint 4 | Ssprint 5 | Ssprint 6 | Ssprint 7 | Ssprint 8 | Ssprint 9 | Ssprint 10 | Ssprint 11 | Ssprint 12 | Ssprint 14 | Ssprint 15 |  | Phase | Duration | person days
.Net Dev | [10 empty] | 1 | 1 | 1 | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
.Net Dev | [10 empty] | 1 | 1 | 1 | bar: Sprint 1 to Stabilization Sprint Sprint 9
Power App Dev 1 | [10 empty] | 1 | 1 | 1 | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
Power App Dev 2 | [10 empty] | 1 | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
DevOps | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Tester 1 | [10 empty] | 1 | 1 | 1 | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
Tester 2 | [10 empty] | 1 | 1 | 1 | bar: Stabilization Sprint Sprint 6 to Stabilization Sprint Sprint 9
Total Resources | 4.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 3.5 | 3.5
|  |  | Sum of Sprint 0 | Sum of Sprint 1 | Sum of Sprint 2 | Sum of Sprint 3 | Sum of Sprint 4 | Sum of Sprint 5 | Sum of Sprint 6 | Sum of Sprint 7 | Sum of Sprint 8 | Sum of Sprint 9 | Sum of Sprint 10 | Sum of Sprint 11 | Sum of Sprint 12 | Sum of Sprint 14 | Sum of Sprint 15
|  |  | 9 | 9 | 11 | 11 | 11 | 11 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 7 | 7
Values
|  |  | Sprint 0 | 4.5
|  |  | Sprint 1 | 5.5
|  |  | Sprint 2 | 5.5
|  |  | Sprint 3 | 5.5
|  |  | Sprint 4 | 5.5
|  |  | Stabilization Sprint 1 | 5.5
|  |  | Sprint 6 | 6.5
|  |  | Sprint 7 | 6.5
|  |  | Sprint 8 | 6.5
|  |  | Sprint 9 | 6.5
|  |  | Stabilization Sprint 2 | 6.5
|  |  | Sprint 11 | 6.5
|  |  | UAT Support | 3.5
|  |  | GO LIVE Support | 3.5
| Stabilization Sprint Sprint 7: Stabilization Sprint |  | UAT Support |  | GO LIVE Support
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13
.NET Dev 1 | [10 empty] | 1 | 1 | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
.NET Dev 2 | [10 empty] | 1 | 1 | bar: Sprint 1 to Stabilization Sprint Sprint 9
Power App Dev 1 | [10 empty] | 1 | 1 | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
Power App Dev 2 | [10 empty] | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
DevOps | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Tester 1 | [10 empty] | 1 | 1 | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
Tester 2 | [10 empty] | 1 | 1 | bar: Sprint 6 to Stabilization Sprint Sprint 9
Total Resources | 4.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 3.5 | 3.5
| Stabilization Sprint Sprint 7: Stabilization Sprint |  | UAT Support |  | GO LIVE Support
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13
Development
System Testing

## EDP-Estimate
Insights Demand Creation App |  | Tablet/Desktop Device
Sr. No. | Screens | Comments | Development Size | Only UI Design Estimate (man days) | Integration with Datasource Estimate (man days) | Data fields | Total Estimate (man days)
1 | Splash Screen | 1. continue - Navigate 2. exit - Navigate | Small | 2 | NA |  | 2
2 | Demand Dashboard (List/Search of Demands) | 1. Search - show only message "feature is not yet available ….." 2. List 3. Create new demand - Navigate 4. Exit - Navigate | Medium | 3 | 2 |  | 5
3 | Demand Create - Details (with save demand) | 1. 12 fields - only few fields are simple and rest are slightly large 2. Cancel button - Navigate 3. Save button - check for mandatory fields, save and navigate to dashboard screen - Integration with datasource 4. Rendering values selected from other screens e.g. active days and times. | X-Large | 10 | 10 | Fields - Reference (NULL, Non Editable) - Title (Mandatory) - Description (Mandatory) - The Creating User (Non-editable, defaulted to the Current User) - Type (Mandatory) - Ownership Type (Staff Member or Team, Mandatory) - Enabled - (Mandatory, defaulted to Enabled) - Select Active Days and Times (defaulted to all day on every day of the week, Mandatory) - Select Person Selection (Option) - Location Type (Fixed Location / Geographical Area, Mandatory) - Required Activities (At least one entry is mandatory, Required Activity Text and Possible Results for each) - Repeat Intervals (Mandatory) | 20
4 | Demand Create - Select Person (RMS/Manual) | 1. Manual - show only message "feature is not yet available ….." 2. From RMS - Navigate 3. Cancel button - Navigate | Small | 1 | NA |  | 1
5 | Demand Create - Select Person - Search RMS | 1. Person List (hardcoded) 2. Search - based on surname, forename, DOB or RMS ID. Add validations. 3. Exit button - Navigate 4. Select button against each record on the list - Navigate | Medium | 3 | 3 | Person fields: surname, forename, DOB. RMS ID | 6
6 | Demand Create - Select Staff (assumption - lookup) | 1. Staff List (hardcoded) 2. Search - based on Rank, Collar Number and Surname fields. Add validations. 3. Cancel button - Navigate 4. Select button against each record on the list - Navigate | Medium | 3 | 3 | Staff fields: Collar number, surname | 6
7 | Demand Create - Select Location | 1. Fixed - Navigate 2. Area - Navigate 3. Cancel button - Navigate | Small | 1 | NA |  | 1
8 | Demand Create - Select Location - Fixed Location | 1. Fields: i. Search Textfield - show lookup for the matched locations and set pin on the maps ii. Maps - allow user to set pin iii. Radius Textfield 2. Save - save/navigate 3. Cancel button - Navigate | Medium | 5 | 3 | Fixed Location - LocationText, Radius | 8
9 | Demand Create - Select Location - Area Location | 1. Maps - Actions: i. show already selected ii. option to select area - draw polygon iii. Exit - navigate iv. clear v. save - validations/save/navigate 2. Cancel button - Navigate | X-Large | 10 | 4 |  | 14
10 | Demand Create - Select Activities (with save) | 1. Static Activity List 2. Allow user to choose applicable activities for this demand (multi-select) 3. Save - Save/Navigate 4. Cancel button - Navigate | Medium | 3 | 3 |  | 6
11 | Demand Create - Select Activities - Select Actions (with save actions) | 1. Static Response List to be shown for each activity 2. Allow user to choose applicable activities for this demand (multi-select) 3. Save - Save/Navigate 4. Cancel button - Navigate | Medium | 2 | 2 |  | 4
12 | Demand Create - Active Days & Times (with save) | 1. Days of the week 2. Each day will be presented with five options with single select 3. Save button - mandatory validation check, save multiple records and navigate 4. Cancel button | Large | 5 | 5 |  | 10
13 | Demand View - Details (incl any responses). This should be mirror to that of Record View screen of Community Insights | 1. Show summary of the demand (fields for each item is mentioned on pg. 29) 2. View more details - show more fields with the respond button 3. Respond button against each activity - Navigate | Large | 7 | 5 |  | 12
14 | Demand View - Show Response Details | 1. Show list of responses associated to selected activity 2. Close - Navigate | Medium | 2 | 1 |  | 3
Community Insights App |  | Mobile/Tablet Device
15 | Splash Screen | 1. continue - Navigate 2. exit - Navigate | Small | 1 | NA | copy of insight creation app | 1
16 | Map View | 1. Maps - following need to be plotted on the map i. Current location of the device* ii. Any fixed location demands iii. Any geographical area iv. Any tasks - Navigate v. Any investigations - Navigate vi. Any intelligence reports - Navigate vii. Any CAD incidents - Navigate 2. List view - Navigate 3. Exit button - close the app 4. Select Demand for fixed location demand or geographical area demand - Navigate to Record View | X-Large | 15 | 10 | 1. Assumption is to show pins of the nearest fixed location demands? 2. how the locations for tasks, investigations, intelligence and CAD incidents are created and to be shown? Similar to the demand pins? | 25
17 | Map View - Show summary record | 1. Show demand summary 2. More Detail button - Navigate to Record View 2. Close button - Navigate | Small | 3 | 1 |  | 4
18 | List View | 1. Gallery view for the following items (fields for each item is mentioned on pg. 28): - Any fixed location demands - Any geographical area demands that are enabled - Any Tasks - Any Investigations - Any Intelligence reports - Any CAD Incidents 2. Map View - Navigate 3. Exit button - close the app 4. More Detail button against each item - Navigate to Record View 5. all items should also have the distance from current location listed in metres (except Geo Location Demands) | X-Large | 12 | 5 |  | 17
19 | Record View (Demand Details incl any responses) | 1. Show summary of the demand (fields for each item is mentioned on pg. 29) 2. View more details - show more fields with the respond button 3. Respond button - Navigate | Medium | 3 | 3 | similar to Demand View screen of Inisghts Demand Creation app | 6
20 | Demand Response (with save response) | 1. 6 fields to be shown (refer pg. 30) 2. Save Response - mandatory validation check/save/navigate - Integration with datasource 3. Exit - Navigate | Medium | 3 | 3 |  | 6
Common
1 | Choose datasource and design data structure for EDP (Sharepoint or Spreadsheet) |  | Medium | NA | 3 |  | 3
2 | Styling |  | Medium | 5 | NA |  | 5
3 | Unit Testing (integration testing, responsive, flow check, etc) |  | Large | 5 | 5 |  | 10
|  |  |  | Only UI Design Estimate (man days) | Integration with Datasource Estimate (man days) | Data fields | Total Estimate (man days)
|  | Total Dev Efforts |  | 104 | 71 |  | 175
Manual Testing
Sr. No. | Screens | Comments | Development Size | Estimate (man days)
4 | Testing Efforts |  | XX-Large | 25% of total dev effort

## EDP-temp
Questions:
1 | What are the possible demand types? | "Wanted Offender", "ASB - Hotspot Patrol", "Section 60 Authority", "Problem Solving", "Victim Welfare", "DVPO"
2 | can you please send us possible activities per demand type? Also sample/predefined activities with the associated actions?
3 | What is the difference between ActivityActions and ActivityResponses? | Ans: Action is to selected from predefined actions, while response is the text that user enters
4 | Sample/Predefined activities with the associated responses? | Not a valid question
5 | What are the below entities and how are these generated? tasks, investigations, intelligence and CAD incidents | Think it is similar to demand but for each entity there will be different fields associated. If yes, then do we need to cover this as it is not descibed in detail. | From where these entities are created? Ref: EDP-11-04, EDP-11-05, EDP-11-06, EDP-11-07 These entities need to be shown only on community insights.
6 | In community insights app, once the end user update the actions/responses for all the activities and save, do we treat that the work on that demand is completed and hide that demand from the UI? | Once demand has been actioned on, Do that demand still be showing up on both the apps? If no then what paramater to be used that indicate that demand is completed?
7 | There is no EDP reference (under Requirements section starting from pg. 6) for setting up activities/actions in Insights Demand Creation, so our assumption is below.
8 | What is the use of "RepeatIntervalUnit" and "Repeat Interval" in Demand entity? | Ref: pg. 20, Data Dictionary - Demand table
9 | Showing community insights icon. Assumption is user will create shortcut on desktop and add weblink of powerapp's app | Ref: EDP-01-01
Reference tables for Activity Response
e.g. | DemandType | Activities | Actions
| Wanted Offender | Activity1 | Action1
Action2
Action3
|  | Activity2 | Action4
Action5
Action6
Action7
|  | Activity3 | Action8
Action9
Insights Demand Creation: Setting up Activity/Actions
For each demand -> (step 1) Choose from predefined activities -> (step 2) for each selected activity, choose from predefined actions
e.g. | for demand D1 -> User will choose 2 activities among 4 i.e. Activity1, Activity2 -> for Activity1, User will associate 2 actions among 3 i.e. Action1 and Action2
| Demand | Activities (super user can add activity) | Actions (super user can associate actions)
| D1 (having type "Wanted Offender") | Activity1 | Action1
Action2
|  | Activity2 | Action4
Action5
Action6
Community Insights
For each demand -> User will view all the activities that was setup in step 1 -> For each selected activity, user can just enter response text
e.g. | for demand D1 -> User will see Activity1 -> User will select each action and add response text
| Demand | Activities | Actions | ResponseText (end user can just add response text)
| D1 (having type "Wanted Offender") | Activity1 | Action1 | add some response
|  |  | Action2 | add some response
|  | Activity2 | Action4 | add some response
|  |  | Action5 | add some response
|  |  | Action6 | add some response
Challenges - Need to spend time to cater this requirement
Sr. no. | Requirements | Description
1 | Show app icon on mobile/tab Show app icon on desktop | Need to check if we can create native app from powerapps for mobile devices?
2 | show/select/store polygon (area location) on maps | Need to understand the return type of the selected area (or polygon) and see how we can show distance of current device location with the selected polygon area.
4 | Choosing correct datasource for EDP. Sharepoint or spreadsheet? | Need to explore correct datasource that can provide solutions for below 1. save/search from different tables/entities 2. store/filter locations 3. search 4. store person image