## Sheet1
Task | Sub-Task | Comments | Estimate (man days)
Admin Console - Screens | Manage Demand Configuration | 13 parameters - 7 medium and rest are simple | 30
| Manage Insights Configuration | 6 parameters - all simple | 5
| Manage Shared / Solution Config | 3 parameters - all medium | 2
| Portal Configuration | 1 parameter - simple | 1
| Broker Configuration | 5/6 parameters - simple Can't test as connector integration is not part of phase 1 | 4
| Splash Screen Configurations for 2 apps | superuser and user | 14
| Log actions/errors/warning | for all the above screens | 30
APIs for SQL (Will finalise in sprint 0) | APIs | 60 | 80
|  | SQL Scripts | 0
Common | Audit/Logging & View | Need to go through existing code and may need to rewrite similar for this project. Audit/Logging will be common for Admin Console & 2 PowerApps | 60
| Dataverse (or SQL) DB Design | Entities Creation | 15
| Software Documentation |  | 0
PowerApps - Common | Env Setup |  | 5
| Custom Connectors | For License Manager, Audit/Logging & for APIs (if developed with SQL) | 30
| Loading configurations | Checking PowerApp Configurations before loading screens | 10
PowerApps - Demand Insignts (Super User) | Login/Licence Manager Check |  | 10
| Splash Screen |  | 10
| Demand - List/Filtering/Sorting |  | 15
| Demand - List Maps |  | 30
| Demand - Create/Edit |  | 25
| Log actions/errors/warning |  | 15
PowerApps - Community Insights (User) | Login/Licence Manager Check | assuming most of the things will be reused from super-user screens | 5
| Splash Screen | assuming most of the things will be reused from super-user screens | 5
| Demand - List/Filtering/Sorting | assuming most of the things will be reused from super-user screens | 10
| Demand - List Maps | assuming most of the things will be reused from super-user screens | 25
| Demand - Edit | assuming most of the things will be reused from super-user screens | 15
| Log actions/errors/warning | assuming most of the things will be reused from super-user screens | 15
Dev Efforts |  |  | 466
Unit Testing & Integration Testing (10% of total dev efforts) | 60 |  | 46.6
Manual Testing (30% of Dev + Unit testing) |  |  | 153.78
DevOps (fixed) |  |  | 100
Total Estimate |  |  | 766.38

## Sheet3
Stabilization Sprint
|  |  | Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14 | Sprint 15 | Sprint 16 | Sprint 17 | Sprint 18
PowerApps - Common | Env Setup, Custom Connectors, Loading configurations | 5
Admin Console - Screens | Manage Demand Configuration | 30
| Manage Insights Configuration | 5
| Manage Shared / Solution Config | 2
| Portal Configuration | 1
| Broker Configuration | 4
| Splash Screen Configurations for 2 apps | 14
| Log actions/errors/warning | 30
0
Common | Audit/Logging & View | 60
| Dataverse (or SQL) DB Design | 15
| Software Documentation | 0
PowerApps - Demand Insignts (Super User) | Login/Licence Manager Check | 10
| Splash Screen | 10
| Demand - List/Filtering/Sorting | 15
| Demand - List Maps | 30
| Demand - Create/Edit | 25
| Log actions/errors/warning | 15
PowerApps - Community Insights (User) | Login/Licence Manager Check | 5
| Splash Screen | 5
| Demand - List/Filtering/Sorting | 10
| Demand - List Maps | 25
| Demand - Edit | 15
| Log actions/errors/warning | 15
Dev Efforts |  | 341
|  |  | Sprint 3: Stabilization Sprint | UAT Support | GO LIVE Support
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14
.Net Dev | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
.Net Dev |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Power App Dev 1 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Power App Dev 2 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
DevOps | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Tester 1 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Tester 2 | Stabilization Sprint Sprint 6: 10; Stabilization Sprint Sprint 7: 10; Stabilization Sprint Sprint 8: 10; Stabilization Sprint Sprint 9: 10 | 10 | 10

## Delivery Plan
Stabilization Sprint
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11
PowerApps - Common (Env Setup, Custom Connectors, Loading Configurations, etc) | bar: Sprint 0 to Sprint 1
Dataverse (or SQL) DB Design | bar: Sprint 0 to Sprint 2
Admin Console - Screens
Manage Demand Configuration | bar: Sprint 3 to Sprint 4
Manage Insights Configuration | bar: Stabilization Sprint Sprint 6 to Stabilization Sprint Sprint 7
Manage Shared / Solution Config | bar: Stabilization Sprint Sprint 6 to Stabilization Sprint Sprint 7
Portal Configuration | bar: Stabilization Sprint Sprint 6 to Stabilization Sprint Sprint 7
Broker Configuration | bar: Stabilization Sprint Sprint 7 to Stabilization Sprint Sprint 8
Splash Screen Configurations for 2 apps | bar: Stabilization Sprint Sprint 5 to Stabilization Sprint Sprint 9
Log actions/errors/warning | bar: Sprint 3 to Stabilization Sprint Sprint 9
Audit Logging and Viewing
PowerApps - Demand Insignts (Super User)
Login/Licence Manager Check | bar: Sprint 2
Splash Screen | bar: Sprint 3
Demand - List/Filtering/Sorting | bar: Sprint 3 to Sprint 4
Demand - List Maps | bar: Sprint 4 to Stabilization Sprint Sprint 6
Demand - Create/Edit | bar: Stabilization Sprint Sprint 7 to Stabilization Sprint Sprint 8
Log actions/errors/warning | bar: Stabilization Sprint Sprint 6 to Stabilization Sprint Sprint 8
PowerApps - Community Insights (User)
Login/Licence Manager Check | bar: Stabilization Sprint Sprint 9
Splash Screen | bar: Stabilization Sprint Sprint 9
Demand - List/Filtering/Sorting | bar: Stabilization Sprint Sprint 9
Demand - List Maps
Demand - Edit
Log actions/errors/warning
| Stabilization Sprint Sprint 5: Stabilization Sprint | Stabilization Sprint
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 |  | Expected Delivery to UAT
PowerApps - Common (Env Setup, Custom Connectors, Loading Configurations, etc) | [13 empty] | PowerApps - Common (Env Setup, Custom Connectors, Loading Configurations, etc) | bar: Sprint 0 to Sprint 1
Dataverse (or SQL) DB Design | [13 empty] | Dataverse (or SQL) DB Design | bar: Sprint 0 to Sprint 2
Admin Console - Screens | [13 empty] | Admin Console - Screens
Manage Demand Configuration | [13 empty] | Manage Demand Configuration | bar: Sprint 3 to Sprint 4
Manage Insights Configuration | [13 empty] | Manage Insights Configuration | bar: Stabilization Sprint Sprint 6 to Stabilization Sprint Sprint 8
Manage Shared / Solution Config | [13 empty] | Manage Shared / Solution Config | bar: Stabilization Sprint Sprint 6 to Stabilization Sprint Sprint 8
Portal Configuration | [13 empty] | Portal Configuration | bar: Stabilization Sprint Sprint 6 to Stabilization Sprint Sprint 8
Broker Configuration | [13 empty] | Broker Configuration | bar: Stabilization Sprint Sprint 7 to Stabilization Sprint Sprint 8
Splash Screen Configurations for 2 apps | [13 empty] | Splash Screen Configurations for 2 apps | bar: Stabilization Sprint Sprint 5 to Stabilization Sprint Sprint 9
Log actions/errors/warning | [13 empty] | Log actions/errors/warning | bar: Sprint 3 to Stabilization Sprint Sprint 9
Audit Logging and Viewing | [13 empty] | Audit Logging and Viewing
PowerApps - Demand Insignts (Super User) | [13 empty] | PowerApps - Demand Insignts (Super User)
Login/Licence Manager Check | [13 empty] | Login/Licence Manager Check | bar: Sprint 2 to Sprint 3
Splash Screen | [13 empty] | Splash Screen | bar: Sprint 3 to Sprint 4
Demand - List/Filtering/Sorting | [13 empty] | Demand - List/Filtering/Sorting | bar: Sprint 3 to Sprint 4
Demand - List Maps | [13 empty] | Demand - List Maps | bar: Sprint 4 to Stabilization Sprint Sprint 6
Demand - Create/Edit | [13 empty] | Demand - Create/Edit | bar: Stabilization Sprint Sprint 7 to Stabilization Sprint Sprint 8
Log actions/errors/warning | [13 empty] | Log actions/errors/warning | bar: Stabilization Sprint Sprint 6 to Stabilization Sprint Sprint 8
PowerApps - Community Insights (User) | [13 empty] | PowerApps - Community Insights (User)
Login/Licence Manager Check | [13 empty] | Login/Licence Manager Check | bar: Stabilization Sprint Sprint 9
Splash Screen | [13 empty] | Splash Screen | bar: Stabilization Sprint Sprint 9
Demand - List/Filtering/Sorting | [13 empty] | Demand - List/Filtering/Sorting | bar: Stabilization Sprint Sprint 9
Demand - List Maps | [13 empty] | Demand - List Maps
Demand - Edit | [13 empty] | Demand - Edit
Log actions/errors/warning | [13 empty] | Log actions/errors/warning

## Loading with Dataverse (hidden)
Actual
| .NEt Developers |  | 160 |  | 240
| Unit Testing |  | 46
| Power App |  | 210 |  | 240
| DevOps |  | 100
Testers
[6 empty] | Stabilization Sprint | [6 empty] | UAT Support | GO LIVE Support |  |  | Effort
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Phase | Duration | person days
.Net Dev | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | Sprint 0 | 2 weeks | 45
.Net Dev |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  | Development efforts | 22 weeks | 655
Power App Dev 1 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | UAT Support | 2 weeks | 35
Power App Dev 2 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  | GO LIVE Support | 2 weeks | 35
DevOps | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | Total | 28 weeks | 760
Tester 1 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Tester 2 | Stabilization Sprint Sprint 6: 10; Stabilization Sprint Sprint 7: 10; Stabilization Sprint Sprint 8: 10; Stabilization Sprint Sprint 9: 10 | 10 | 10
| Stabilization Sprint Sprint 5: Stabilization Sprint |  |  | UAT Support | GO LIVE Support |  |  | Effort
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Phase | Duration | person days
.Net Dev | [10 empty] | 1 | 1 | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
.Net Dev | [10 empty] | 1 | 1 | bar: Sprint 2 to Stabilization Sprint Sprint 9
Power App Dev 1 | [10 empty] | 1 | 1 | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
Power App Dev 2 | [10 empty] | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
DevOps | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Tester 1 | [10 empty] | 1 | 1 | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
Tester 2 | [10 empty] | 1 | 1 | bar: Stabilization Sprint Sprint 6 to Stabilization Sprint Sprint 9
Total Resources | 4.5 | 4.5 | 5.5 | 5.5 | 5.5 | 5.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 3.5 | 3.5

## loading with SQL+Dataverse
Actual
| .NEt Developers |  | 160 |  | 240
| Unit Testing |  | 46
| Power App |  | 210 |  | 240
| DevOps |  | 100
Testers
[5 empty] | Stabilization Sprint |  |  |  |  | Stabilization Sprint |  |  | UAT Support | GO LIVE Support |  |  |  | Effort
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 |  | Phase | Duration | person days
.Net Dev | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  | Sprint 0 | 2 weeks | 45
.Net Dev |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  |  | Development efforts | 22 weeks | 670
Power App Dev 1 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  | UAT Support | 2 weeks | 35
Power App Dev 2 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  |  | GO LIVE Support | 2 weeks | 30
DevOps | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  |  | Total | 28 weeks | 780
Tester 1 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Tester 2 | Stabilization Sprint Sprint 5: 10; Stabilization Sprint Sprint 6: 10; Stabilization Sprint Sprint 7: 10; Stabilization Sprint Sprint 8: 10; Stabilization Sprint Sprint 9: 10 | 10 | 10
100200
[16 empty] | 91200 |  | 670
| Stabilization Sprint Sprint 5: Stabilization Sprint | Stabilization Sprint |  |  | UAT Support | GO LIVE Support |  |  |  | Effort
| Ssprint 0 | Ssprint 1 | Ssprint 2 | Ssprint 3 | Ssprint 4 | Ssprint 5 | Ssprint 6 | Ssprint 7 | Ssprint 8 | Ssprint 9 | Ssprint 10 | Ssprint 11 | Ssprint 12 | Ssprint 14 | Ssprint 15 |  | Phase | Duration | person days
.Net Dev | [10 empty] | 1 | 1 | 1 | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
.Net Dev | [10 empty] | 1 | 1 | 1 | bar: Sprint 1 to Stabilization Sprint Sprint 9
Power App Dev 1 | [10 empty] | 1 | 1 | 1 | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
Power App Dev 2 | [10 empty] | 1 | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
DevOps | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Tester 1 | [10 empty] | 1 | 1 | 1 | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
Tester 2 | [10 empty] | 1 | 1 | 1 | bar: Stabilization Sprint Sprint 6 to Stabilization Sprint Sprint 9
Total Resources | 4.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 3.5 | 3.5
|  |  | Sum of Sprint 0 | Sum of Sprint 1 | Sum of Sprint 2 | Sum of Sprint 3 | Sum of Sprint 4 | Sum of Sprint 5 | Sum of Sprint 6 | Sum of Sprint 7 | Sum of Sprint 8 | Sum of Sprint 9 | Sum of Sprint 10 | Sum of Sprint 11 | Sum of Sprint 12 | Sum of Sprint 14 | Sum of Sprint 15
|  |  | 9 | 9 | 11 | 11 | 11 | 11 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 7 | 7
Values
|  |  | Sprint 0 | 4.5
|  |  | Sprint 1 | 5.5
|  |  | Sprint 2 | 5.5
|  |  | Sprint 3 | 5.5
|  |  | Sprint 4 | 5.5
|  |  | Stabilization Sprint 1 | 5.5
|  |  | Sprint 6 | 6.5
|  |  | Sprint 7 | 6.5
|  |  | Sprint 8 | 6.5
|  |  | Sprint 9 | 6.5
|  |  | Stabilization Sprint 2 | 6.5
|  |  | Sprint 11 | 6.5
|  |  | UAT Support | 3.5
|  |  | GO LIVE Support | 3.5
| Stabilization Sprint Sprint 7: Stabilization Sprint |  | UAT Support |  | GO LIVE Support
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13
.NET Dev 1 | [10 empty] | 1 | 1 | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
.NET Dev 2 | [10 empty] | 1 | 1 | bar: Sprint 1 to Stabilization Sprint Sprint 9
Power App Dev 1 | [10 empty] | 1 | 1 | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
Power App Dev 2 | [10 empty] | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
DevOps | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Tester 1 | [10 empty] | 1 | 1 | 1 | 1 | bar: Sprint 0 to Stabilization Sprint Sprint 9
Tester 2 | [10 empty] | 1 | 1 | bar: Sprint 6 to Stabilization Sprint Sprint 9
Total Resources | 4.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 3.5 | 3.5
| Stabilization Sprint Sprint 7: Stabilization Sprint |  | UAT Support |  | GO LIVE Support
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13
Development
System Testing